## Sheet1
|  | Project Name: | Inventory Management System
|  | Project Description: | Create an application (inventory management system) for an end user to interact with via a command line interface.
|  | Project Owner: | Aswene Sivaraj
Risk ID | Date registered | Risk area | Risk description | Probability |  | Risk Level |  |  | Project impact | Proximity / Length of impact | Response strategy
1 | 01.04.2020 | Illness/Injury | Developer lacks mobility and is unable to start or continue or finish the project. |  | M |  | M |  | Workload bulds-up and if developer does not recover before project deadline, project is incomplete. | Short term but variable depending on illness. | Avoid or limit human contact to bare necessities.
2 | 01.04.2020 | Time management | Time allocated to each aspect of the project not clearly defined. |  | M |  |  | H | Overlap of individual feature timelines which creates a backlog and delay in project completion. | Long term. | Create a realistic deadline for each feature to be designed.
3 | 07.04.2020 | Hardware unavailability | Hardware performance is insufficient due to faulty or damaged equipment, i.e. laptop, computer,etc. | L |  |  |  | H | Fall behind deadlines due to unavailability of hardware to do work. Possible loss of data if hardware damaged. | Medium term issue and instance of occurrence unpredictable. | Contingency: continuous back-ups of project to avoid data loss and safeguard hardware to minimise risk of damage.
4 | 07.04.2020 | Inadequate skills and knowledge | Insufficient practice on programming language and mediocre knowledge of technologies to be used. |  | M |  | M |  | Low quality project developed, many of the requirements are not met. | Short term, initial stage of the project or for new implementations. | Research practices required for implementation of new features.
5 | 07.04.2020 | Misunderstanding project scope | Not reading and identifying the requirements correctly. | L |  |  |  | H | Objectives not met may result in redoing the project or failing. | Early stages, beginning of the project when objectives are stated. | Clarify requirements if not understood. Project completed to the given requirements.
6 | 16.04.2020 | Design flaws | Errors in entity relationship diagram (ERD). Relationships between entities incorrectly defined. | L |  |  | M |  | Database and its tables created incorrectly. | Short term impact. Issue would be identified when inputting data to the databases tables. | Design an ERD which immitates the databases tables correctly and test it before advancing in the project.
7 | 16.04.2020 | Access to online platforms | Low quality or no internet connection prevents accessing online cloud platforms such as GCP and nexus. | L |  | L |  |  | Unable to connect to database and view information in the tables to see if JAVA code works correctly. Unable to push files to nexus. | Short term issue, but unpredictable. | Avoid: Reduce internet usage of other devices. Use mySQL workbench on device whenever internet is down.
8 | 25.04.2020 | Git push | Unable to upload files to the git repository. | L |  | L |  |  | Delays in uploading working features. | Short term. | Avoid: Only upload from a single device to avoid merge conflicts.
9 | 27.04.2020 | Testing failures | Low coverage of testing for the code developed. |  | M |  |  | H | Application not functioning as required so project requirements not met. | Medium term. | Solve: Errors in code require refactoring to be able to pass the tests.
10 | 29.04.2020 | Presentation questions | Not well prepared to answer questions. | L |  | L |  |  | Understanding of project appears to be low and unable to explain the project to a high standard. | Short term, occuring at the end of the project. | Recap everything done to date to reaffirm understanding.