## Sheet1
|  | Project Name: | Inventory Management System
|  | Project Description: | Create an application (inventory management system) for an end user to interact with via a command line interface.
|  | Project Owner: | Aswene Sivaraj
Risk ID | Date registered | Risk area | Risk description | Probability |  | Risk Level |  |  | Project impact | Proximity / Length of impact | Response strategy
1 | 01.04.2020 | Illness/Injury |  |  | M |  | M |  |  |  | Avoid
2 | 01.04.2020 | Time management | Poor planning. Can start off on track but then fall behind. |  | M |  |  | H | Not meeting deadlines, causing backlog and eventually delay in completion. | Long term | Create a plan with weekly checklists. Project completed on-time or earlier.
3 | 07.04.2020 | Hardware unavailability | Hardware performance is insufficient due to faulty or damaged equipment, i.e. laptop, computer,etc. | L |  |  |  | H | Fall behind deadlines due to unavailability of hardware to do work. Possible loss of data if hardware damaged. | Medium term issue and instance of occurrence unpredictable. | Contingency: continuous back-ups of project to avoid data loss and safeguard hardware to minimise risk of damage.
4 | 07.04.2020 | Inadequate skills and knowledge | Insufficient practice on programming language. Mediocre knowledge of technologies to be used. |  | M |  | M |  | Project completed incorrectly or project incomplete. | Primarily in the early stages but may occur at any stage throughout the project. | Enhance skills through additional practice. Improve knowledge through further research. Improved skills and knowledge to be able to complete the project.
5 | 07.04.2020 | Misunderstanding project scope | Not reading the requirements properly. | L |  |  |  | H | Objectives not met may result in redoing the project or failing. | Early stages, beginning of the project when objectives are stated. | Clarify requirements if not understood. Project completed to the given requirements.
6 | 16.04.2020 | Design flaws | Errors in entity relationship diagram (ERD). Relationships between entities incorrectly defined. | L |  |  | M |  | Relationship and access between data tables incorrectly defined. | During the creation of the ERD. | Additional research. Consult to confirm understanding. Less chance of oversights in the database.
7 | 16.04.2020 | Access to online platforms | Low quality or no internet connection prevents accessing online cloud platforms such as GCP and nexus. | L |  | L |  |  | Build-up of work to do. Increase workload causing overworking. | Unknown. Unpredictable. | Reduce internet usage of other devices. Keep some mobile data as back up to use. If connection fails, project timeline remains unaffected.
8 | 25.04.2020 | Git
9
10
11